## Instructions
Step | Instructions
1 | Create a copy of this sheet and name the sheet as "SOW Name" - "Estimation". For example, if the SOW name is "Client Payment Automation" the name of this sheet will be "Client Payment Automation - Estimation". The copy of this sheet needs to be saved in the project folder that was created for this estimator.
2 | Complete Functional tab.
3 | Complete Technical NetSuite tab.
4 | Complete Integration tab.
5 | Go to Summary tab.
6 | Input Hourly Rate
7 | Input PM %
8 | Copy the estimation table from the SOW Summary tab and paste as image in the SOW.
9 | Send estimation sheet and SOW to Ethos Director for approval.

## Detailed Summary
Estimated Hours and Fees
Phase | Area |  |  | Total
| Functional | Technical | Integration
Design | 12 | 12 | 12 | 36
Configuration | 27 | - | - | 27
Development | - | 38 | 38 | 76
UAT | 6 | 16 | 16 | 38
Training | 4 | 0 | 0 | 4
Cutover | 8 | 8 | 8 | 24
Support | 6 | 11 | 11 | 28
Project Oversight 15% | 9.45 | 12.75 | 12.75 | 34.95
Hourly Totals | 72 | 98 | 98 | 268
Estimated Fees (Standard Rate: $300 ¦ Discounted Rate: $255) | 21600 | 29400 | 29400 | 68340
Project Oversight %
15%
Standard Hourly Rate
300
Discount
15%
Discounted Hourly Rate
255
Standard Total Text
Estimated Fees (Standard Rate: $300)
Discounted Total Text
Estimated Fees (Standard Rate: $300 ¦ Discounted Rate: $255)
Note on B17: All projects should have at least 10% of oversight. Oversight includes status meetings, budget management, and Ethos internal quality control. More difficult clients or clients that require extensive follow-up, need to have PO% at least 15%.
Note on B20: Input hourly rate for project.
Note on B23: If a discount has been applied to this client's standard hourly rate or if this specific project is being discounted, enter the discount here. For example, if the client receives a 15% discount on their standard hourly rate, enter 15 here.

## SOW Summary
Estimated Hours and Fees
Phase | Total
Design | 36
Configuration | 27
Development | 76
UAT | 38
Training | 4
Cutover | 24
Support | 28
Project Oversight 15% | 34.95
Hourly Totals | 268
Estimated Fees (Standard Rate: $300 ¦ Discounted Rate: $255) | 68340

## Functional
ID | Task | Design | Configuration | UAT | Training | Cutover | Support | Total
EBS.001 | Bundle Install | 0 | 1 | 0 | 0 | 0 | 0 | 1
EBS.002 | WMS System Rules | 2 | 2 | 0 | 0 | 1 | 0 | 5
EBS.003 | SCM Mobile Configuration | 4 | 10 | 0 | 0 | 4 | 0 | 18
EBS.004 | Sales Order Picking Process | 4 | 10 | 2 | 4 | 2 | 4 | 26
EBS.005 | [7 empty] | 0
EBS.006 | [7 empty] | 0
EBS.007 | [7 empty] | 0
EBS.008 | [7 empty] | 0
EBS.009 |  | 2 | 4 | 4 | 0 | 1 | 2 | 13
Total |  | 12 | 27 | 6 | 4 | 8 | 6 | 63
Note on B1: Description needs to be short and concise. This is a title, not a solution explanation.
Note on C1: Complex functional tasks are the only functional tasks that require formal design documents. Otherwise, input the hours required to finalize requirements so that configuration can begin.
Note on D1: Input the hours to configure the task and internally validate the configuration prior to transitioning to client UAT.
Note on E1: Input hours required to demonstrate feature. If a training aid / test script is required, input hours required to document aid.
Note on G1: Input hours required to migrate solution to Production and any post production migration regression testing. Any data migration should be included in this assessment.
Note on H1: Input hours required to support the client once the configuration is migrated to production. Estimate for one to two weeks. Any support duration beyond two weeks needs to be escalated to Ethos senior leadership for discussion.

## Technical NetSuite
ID | Task | Type | Design | Development | UAT | Training | Cutover | Support | Total
EBS.001 | Placeholder 1 | Map/Reduce | 4 | 12 | 4 | 0 | 2 | 4 | 26
EBS.002 | Placeholder 2 | Client | 2 | 6 | 4 | 0 | 2 | 1 | 15
EBS.003 | Placeholder 3 | Workflow Action | 2 | 8 | 4 | 0 | 2 | 2 | 18
EBS.004 | Placeholder 4 | Suitelet | 4 | 12 | 4 | 0 | 2 | 4 | 26
Total |  |  | 12 | 38 | 16 | 0 | 8 | 11 | 85
Note on D1: Input hours required to design the NetSuite script. Estimate should include functional/technical design document that will be passed to development team.
Note on E1: CJ Carter: Input hours required to internally develop the solution.
Note on F1: Input hours required to internally validate the solution, external demonstration, and support client through testing and validation.
Note on G1: CJ Carter: Training is only required if the client requires a technical review of the solution. Typically this will be 0 unless the client explicitly requests.
Note on H1: CJ Carter: Input hours required to migrate the solution to production and hours required to perform regression testing in production.
Note on I1: Input hours required to support the client once the script is migrated to production. Estimate for one to two weeks. Any support duration beyond two weeks needs to be escalated to Ethos senior leadership for discussion.

## Integration
ID | Flow | Method | Frequency | Source System | Source Record | Target System | Target Record | Design | Development | UAT | Training | Cutover | Support | Total
EBS.001 | Placeholder 1 | iPaaS - Prebuilt | Scheduled | Salesforce | Prospect | NetSuite | Customer | 4 | 12 | 4 | 0 | 2 | 4 | 26
EBS.002 | Placeholder 2 | REST API | Real-time | Salesforce | Order | NetSuite | Sales Order | 2 | 6 | 4 | 0 | 2 | 1 | 15
EBS.003 | Placeholder 3 | iPaaS - Custom | Real-time | Salesforce | Shipment | NetSuite | Item Fulfillment | 2 | 8 | 4 | 0 | 2 | 2 | 18
EBS.004 | Placeholder 4 | 3rd Party Connector | Scheduled | Salesforce | Payment | NetSuite | Customer Payment | 4 | 12 | 4 | 0 | 2 | 4 | 26
Total | [7 empty] | 12 | 38 | 16 | 0 | 8 | 11 | 85
Note on I1: CJ Carter: This includes functional and technical design document. If custom RESTlet is being developed, the hours will typically be higher due to increased design, development, and testing. If custom RESTlet is used, detailed field mapping needs to be completed in excel which will be part of design deliverable.
Note on J1: CJ Carter: Input development hours required to complete unit testing for the respective integration flow.
Note on K1: Input hours required to demonstrate integration to client and support the client during their internal validation.
Note on L1: CJ Carter: Training is only required if the client requires a technical review of the solution. Typically this will be 0 unless the client explicitly requests.
Note on M1: CJ Carter: Input hours required to migrate integration to production and perform regression testing in production.
Note on N1: Input hours required to support the integration in production for 1-2 weeks. If more than 2 weeks is required to support the integration, this needs to escalated to Ethos leadership for discussion.

## List Options
Script Types | Integration Methods
Map/Reduce | SOAP API
Mass Update | REST API
Workflow Action | iPaaS - Custom
RESTlet | iPaaS - Prebuilt
Scheduled | 3rd Party Connector
Suitelet | SFTP
User Event
Client